## Slide 1: Integration Tests continued
Mike Lamont

## Slide 2: Integration tests
Ongoing dry runs
  Beam Dump, Injection, PGC
Software tests/dry runs
  From CCC using controls infrastructure and software - check functionality of the individual systems – continous mode
  RF, Collimators, Beam Instrumentation
Experiments
  Communication, magnets…
Machine protection tests
PGC+, PGC++
Machine Protection commissioning
Partial machine checkout
Full machine checkout

## Slide 3: PGC+: Generation
Sort optics etc. out to the full
  details, details (acc, dec, corrections…)
Injection actual settings
  Collimators
  Kickers
Context independent
  Power converter parameters
Pre-cycle, injection, ramp, squeeze, collide, ramp-down
Ramp variations – energy/optics
Squeeze variations
All knobs, bumps
  separation bump
  crossing angle bump
  Q, Q’

## Slide 4: PGC+: FIDEL
Transfer functions for all magnet circuits
Harmonic errors for quads and bends
Decay correction at injection
  all multipoles
Snapback correction at start of ramp
Deploy and check everything we’ve got from Luca & team

## Slide 5: PGC+: Drive
Full cycle tests of all available circuits
  plus RF (test devices), and collimators
  Check and set full parameter space
  Pre-cycle, injection, ramp, squeeze, collide, ramp-down
Establish near-perfect control of power converters
  Circuit limits, parameters…
Test trim (acc, dec, dI/dt…)
  Tune [lattice, correction]
  Chromaticity
  Multipoles
  Separation bumps
  Coupling

## Slide 6: Physics/Experiments Dry Run
Luminosity
  Acquisition and display, BRA application
  Optimization, trims, bumps etc.
  Dry Luminosity Scans
Experiment Instrumentation & signals
  BCMs, Lumi etc.
Experiment communication
  DIP – to & from
  Vetos, Handshakes
Interlocks
  Beam abort, injection inhibit
Magnets
  Alice/LHC dipoles and compensation

## Slide 7: Hardware tests/dry runs
 | Tests
INJECTION KICKERS | Dry run
BEAM DUMP | Dry run
POWER CONVERTERS | PGC[++]
COLLIMATORS | Include in PGC when available
RF | LSA roll out and tests June System available end June for dry runs
TRANVERSE FB | Whenever
MAGNETS | PGC
MKQA , AC dipole etc. | IST
WARM MAGNETS | PGC TI8/2 DR
SPECTROMETERS etc. | Tests in June – LHCb and Alice
MACHINE PROTECTION | Rattle

## Slide 8: RF - LSA
RF_TOTAL_VOLTAGE
RFVOLTAGE_PARTITION
RFVOLTAGE_PHASE
RFVOLTAGE_AMPL
RFVOLTAGE_Q
RFVOLTAGE_I
COUPLER_POS
BUCKET_AREA
MOMENTUM
Value generator 1
Value generator 2
Makerule 1
Makerule 2
Makerule 3
Makerule 4
SYNCH_FREQUENCY
BUCKET_AREA_CALC
DELTAP_P
Makerule 6
Makerule 7
Makerule 5
Value generator 3
Value generator 4
CAVITY CONTROLLER
Cavity_Q
Makerule 12

## Slide 9: Objectives – Hardware - generics
 | Application | XPOC | Analog Acquisition | Alarms | SIS | MCS | PM | Timing | RBAC
INJECTION KICKERS | X |  | X | X |  | X | X | X | X
BEAM DUMP | X | X | X | X |  | X | X | X | X
POWER CONVERTERS | XX |  |  | X | X |  | X | X | X
COLLIMATORS | X |  |  | X | X | X | X | X | X
RF | XX |  | X | X | X |  | X | X | X
TRANVERSE FB | X |  | X | X |  |  | X | X | X
MAGNETS | XX |  |  | X |  |  | X |  | 
MKQA etc | X |  |  | X | X |  | X | X | X
WARM MAGNETS | X |  |  | X | X |  | X | X | X
RADIATION MONITORS |  |  |  | X |  |  | X |  | 
SPECTROMETERS |  |  |  | X | X |  | X | X | 

## Slide 10: Software tests
http://lhc-commissioning.web.cern.ch/lhc-commissioning/dry-runs/systems/software-tests.htm
Plus a test environment

## Slide 11: PGC++ - sectors 78 and 81
Machine Protection
  BIS to BLM, BIS to PIC, BIS to LHCb, BIS to injection
LHCb
  Dipole and compensators, Communication with Experiment
Nominal Cycle
  2 sectors: pre-cycle, injection, ramp, squeeze plus septa/end TI8
Injection
  TDI, Kickers, BI, End TI8
Beam Instrumentation
  BPM, BLM,
Natural lead in to an injection test
Extended test of two cold sectors

## Slide 12: Schedule