## Slide 1: Sector 56 – preliminary plans for tests
Gianluigi for the Machine Check-Out Team
(Mike, Reyes, Rossano)

## Slide 2: Status of Sector 56
By this afternoon final test on the “overheated” bend in Sector 56 should be completed:
  Quench at 2 kA of the magnet
  Ramp to nominal current of the RBs
If the test is OK for MPP  we take over the sector
Power converters in the arc and UA63 will be unblocked either this afternoon or tomorrow morning.

## Slide 3: Power converters that will not be available
Triplet Correctors:
  RCBXH1.R5
  RCBXH2.R5
  RCBXH3.R5
  RCBXV1.R5
  RCBXV2.R5
  RCBXV3.R5
  RCOSX3.R5
  RCOX3.R5
  RCSSX3.R5
  RCSX3.R5
  RCTX3.R5
  RQSX3.R5
Should be available (being checked with HWC)
  RQ4.L6
  RCO.A56B1
  RCBCV10.L6B1

## Slide 4: Issues
Still quite some activity ongoing in the Sector (Mirko):
  Optical fibres pt. 6
  Alignment of the vacuum chambers in dump lines
  Dump line vacuum
  Shielding Q5
  Bake-out of CMS vacuum chamber
  Other activities for experiments (ZDC,TOTEM)
  TIM installation
  MSD gaussmeter
  Installation of protections for power converters in RR57
  Power converter performance and debugging (corr., ROD)
  BLM tests

## Slide 5: Issues
600 A commissioned with ramp rates and acceleration rates lower than requested (approximately 40 circuits: MQT, MQTL, MS, MQS, etc.)
New QPS SW installed yesterday to overcome this limitation

## Slide 6: Proposal
For this week (3 days left) leave the mornings to complete the works already on-going in the tunnel
In the afternoon go ahead with the tests
To be reviewed at the end of the week: try to go for run the whole day next week
Try to collect remaining interventions and test the following week

## Slide 7: Generation - preparation
Sort optics etc. out to the full
  all circuits
  acceleration, deceleration, dI/dt etc.
Injection
  Magnets, Collimators, Kickers
  FIDEL: decay and snapback
5 TeV ramp
  Latest FIDEL import
5 TeV squeeze
  with 600 A circuits inc. SF/SD
  now acceleration/deceleration aware!
Programmed ramp down
Pre-cycle
  MB, MQ, IPQs…

## Slide 8: Generation - preparation
Context independent
  Power converter parameters
Knobs, bumps
  separation bumps
  crossing angle bumps
  Lumi scan
  Q, Q’,coupling, coulpling compensation
  Harmonics…
RF test devices

## Slide 9: FIDEL
Transfer functions for all magnet circuits
Harmonic errors for quads and bends
Decay correction at injection
  all multipoles
  invoke powering history dependence
Snapback correction at start of ramp
Deploy and check everything we’ve got from Luca & team

## Slide 10: Cycle
Pre-cycle, injection, ramp, squeeze, collide, ramp-down
Powering history, decay & snapback
Possible ramp variations – energy/optics
Squeeze variations
  Check acceleration, deceleration
  Stop in squeeze, trim, incorporate and carry on
Pre-cycle | MB, MQ, IPQs | 1 day | 
Ramp | All circuits | 2 hours | shouldn’t be an issue
Squeeze | IPQs plus 600 A | 1 day | acc/dec plus stop in squeeze etc
Injection plateau | decay & trims | 1 day | FIDEL/powering history Trim parameter space
Collide |  | 0.5 day | Bumps off

## Slide 11: Trim Tests
Full parameter space 
CTRIM – drive – test thoroughly
Incorporation
Trim
  at injection
  ramp and squeeze functions [check limits]
  flat top
  during squeeze after squueze
Test circuit limits [d2I/dt2 etc.]

## Slide 12: Trim
System | Comment | Circuits | Knob there
Momentum – sector 56 | full rescale | all | Y
Tune |  | MQ | Y
Tune-correction |  | MQT | Y
Chromaticity |  | MS | Y
Coupling |  | MQS | 
Separation bump | MAD | Various correctors | Y
Crossing bump | MAD | Various correctors | 
Lumi bumps |  | Various correctors | Y - Simon
b1 – momentum per arc |  | correctors | ish
b2 |  | MQT | Y
b3 |  | MCS | Y
b4 |  | MCO | Y
b5 |  | MCD | Y
Orbit correctors | YASP | all correctors | Y

## Slide 13: Other
SIS
Machine Protection Tests
Beam Instrumentation Tests
  Test BLM threshold management (Greg) – week 27
Logging, alarms, fixed displays
Trigger acquisition – ready to test
Sequencer
Run Control
  Mode, fill number, handshakes
Timing
Experiment Instrumentation & signals
Experiment communication – DIP
  extend the list – BPMs,

## Slide 14: Tests 1/3
Wednesday 17/06 - Thursday 18/06 PM:
  600 A acceleration rates and ramp rates to nominal (Reyes, Rossano, Gianluigi)
  Support from MPP (with low priority) might be needed – Walter will help while on shift
  LSA Trim Tests
Friday 19/06 PM:
  Generation of ramp and squeeze with achieved parameters for the 600 A and ramp and squeeze of the whole lot (Mike, Reyes)
  Alarm and SIS verification (parasitic) (Gianluigi, Luis, Markus, Rossano)

## Slide 15: Tests 2/3
Monday 23/06 – Tuesday 24/06 (Mike, Massimo, Ralph, Stephane):
  Test pre-cycle
  At injection test decay corrections and snap-back
  Ramp (with snap-back corrections) and squeeze
  Test of chromaticity, tune, aperture bumps, crossing / separation bumps, coupling trims fully squeezed
  Simulation of tune, orbit feedback
  Alarm and SIS verification (evenings, Gianluigi, Markus, Rossano)
  In parallel heat load measurements on cryo-system (Serge)
No rush – will cover what is possible – more time will be required

## Slide 16: Tests 3/3
Wednesday 25/06:
  RB-QF-QD tracking (AB/PO – ½ day)
  SIS tests for Power converters (Rossano, Gianluigi)
Thursday 26/06:
  RB performance without active filter (AB/PO – 1 day)
We will have regular meetings in the glass box at 17:00 from tomorrow

## Slide 17: Week 27
Cryogenics tests (no powering possible in Sector 5-6 during this tests):
  Cool-down and test of sector 56 quench lines (to P5 and to P6)
  Cold Compressors recovery tests
  Large Quench recovery test
Interventions remaining (compatibility with cryo interventions)