## Slide 1: Injection test?
Mike Lamont
For initial discussion

## Slide 2: Possible scenario
 | Phase | Time
Mid July | All sector colds | 
 | Couple of weeks for cryo stabilization etc Recovery from UX85 intervention | 
End July | DSO tests, close ring | 2 days
Early August | Injection test | 2 days - weekend
Day after | Radiation survey, establish supervised areas | 1 day
August | Hardware commissioning of last sectors | 2 weeks
August | Machine checkout | 2 weeks
Weekend (Friday evening to Monday morning)
~ 4 weeks before full commissioning

## Slide 3: Access
Ring fully closed
DSO tests appropriate to injection test scenario
Experiments out for a week-end
  “a disturbance but acceptable” – clearly to be confirmed
Access during test possible
  to areas that don’t see beam
General access mode following test
  where appropriate

## Slide 4: Access – DSO tests
Goal
  Nominal system deployed and tested before end July
Plan evening shifts for one week in July
  2 points an evening
  test doors [350] – sample or all
  by-pass safety elements to avoid hitting them too often, check receipt of signals etc.
  by-pass BIW
Plus one weekend of test
Resources required
  Personnel for test, documentation etc.
Ghislain Roy

## Slide 5: DSO – Injection Test
Close whole ring
Test all doors in 7 & 8 against injection chain
Qualify rest of ring against injection chain
Condem main power supplies down-stream (block beam)
Potentially interesting option acting as useful milestone

## Slide 6: Radiation
Supervised areas after test
  Given analysis, and measurements during and after the test, it is envisaged that:
  Certain areas might be declared controlled areas for the first few days after the test;
  Thereafter these areas would join the rest of the sectors involved as supervised areas
Not really an issue at this stage.
LHCb – presumably ready to accept beam by this stage

## Slide 7: Option 1: Injection R8 – A78 – R7
No temporary dump to be installed at IR7 - use collimators instead (3 primaries, 5 secondaries for the single beam)
  detailed proposal in place (Stefano)
No temporary installation of beam instrumentation at IR7.
Need small part of 8-1, all 7-8 hardware commissioned to 450 GeV+.
Minimal Impact Solution

## Slide 8: Option 1: Pros and Cons
Minimal requirements on Cryogenics & HWC
Less area classified by RP
Less impact on other systems
  BI, LBDS
Only one sector test - less systems tested
  BI, LBDS, collimators missed
BI configuration not perfect
  Rely on in situ instrumentation
  Not ideal – no BCT – some implications for measurements

## Slide 9: Option 2: Injection R8 – A78 – A67 – Dump
Use TCDQ and TCS to block down stream aperture – safeguard only - no installation of temporary dump. RP approval/study required
Beam onto TDE – LBDS/B2 will be ready for action
Can use correctors to steer into dump channel - so should be able to guarantee very little beam goes onto TCDQ etc.
Rely on in situ instrumentation (BCT in dump line etc.). No temporary installation required.
Need small part of 8-1, all 7-8, all 6-7 hardware commissioned to 450 GeV+.

## Slide 10: Option 2: Pros & Cons
Test beam dump and related systems
Don't irradiate ring - beam onto TDE (beam dump block)
Check IR7 optics, performance of warm magnets
Beam through 3 IRs, 2 full sectors
Full suite of Beam Instrumentation in place
  FBCT, Screens, BLMs
Support required for 3 cold sectors cold – sectors should be operational anyway
Favoured Solution

## Slide 11: Option 3 – Injection point 2 – B1
Need partial 1-2, complete 2-3
Dump on collimators in IR3
  scheme sketched by Stefano
Could do both B1 and B2!
But demands on Access/DSO tests would be greater.

## Slide 12: Proposed Tests

## Slide 13: Tests
Pilot Beam for the most part:
  single bunch of 5 - 10 x 109 protons
Total intensity:
  ~ 1013 protons
Gives a first good look at:
  Full injection set-up
  Instrumentation
  Aperture
  Field quality, polarities
No doubt we would learn a lot – some lead-in time for problem resolution

## Slide 14: Monitoring
Radiation monitoring
  RAMSES operational
  LHCb: 4-5 monitors planned under RAMSES
Beam Loss Monitors
  Sensitive to losses at 1% level with pilot bunch intensity
Beam Intensities
  Beam extracted, injected (and to dump) to be logged
RPG survey after the event and perhaps during the test to ensure that activation remains low.
  Careful survey afterwards planned after the test near the injection dump and dump itself.

## Slide 15: BIS
BIC
BIC
BIC
BIC
BIC
BIC
3/16 of LHC Beam Interlock System
SPS Extr.
Kicker
BIC
BIC
BIC
BIC
BIC
BIC
BIC
BIC
BIC
BIC
SPS Extraction Lines
Interlock System
  Radiation levels
  BLM
  Powering Interlock
  Warm Magnet Interlock
  Vacuum
  LHCb
Access system will provide input to BIS which will inhibit SPS extraction. Configurable if the case of extraction required & LHC not ready (e.g. extraction tests)
Old Slide!!! – see Bruno for update

## Slide 16: Other systems
Injection elements: septa, kickers
Collimators
Machine Protection
Beam Instrumentation:
  BPMs, BLMs, BTV, BCT, BST
Magnet Model
Controls
Software/tools
Access system
Radiation Protection
Radiation Monitoring
Optics, aperture model
Test preparation orthogonal to HWC and already ongoing.

## Slide 17: Injectors

## Slide 18: Impact
Fairly limited demands on cold circuits
  Beam 2 & limited recycling
  8-1 and 7-8 already complete, 6-7 starting soon
  Re-cool-down following UX85 intervention required
Cryogenics, QPS, HWC support required during test
  In general, low current levels with occasional cycles
  Sectors concerned would hopefully be operational by then
  Experience from 56
Access
  Experiments – key, would have to sacrifice a few days access
  HWC – commissioning in other sectors can continue (if we’re working weekends) – not an issue for sectors concerned